## Asset Tracker
Page | Section / Component | Asset / Deliverable | Desktop / Landscape | Mobile / Portrait | Poster / Still | On Disk Now | Status | Pri | Notes
HOME PAGE
Home | VideoHero | Hero showreel film | 1920x1080 16:9, 3-5MB, 15-25s loop -> /video/hero-reel.mp4 | 1080x1920 9:16, 1.5-2.5MB -> /video/hero-reel-mobile.mp4 | hero-poster.jpg (1920x1080) + hero-poster-mobile.jpg (1080x1920) | Desktop=placeholder (intro-reel-web); Mobile=herobanner_fast.mp4 (39.7MB!); posters=intro-poster.jpg | In Progress | P0 | Needs a true PORTRAIT re-cut (not a crop). Mobile file is oversized - re-encode to <=2.5MB. herobanner.mp4 (78MB) is unused.
Home | AssetReel | Aerial 360 - loop + poster | n/a (portrait asset) | 720x900 4:5, ~500KB, 4s loop -> /video/asset-reel/aerial-360.mp4 | /images/asset-reel/aerial-360.jpg (720x900, ~100KB) | None (placeholder loop + picsum poster) | Not Started | P1 | Muted 4s loop. Could be re-cut from the new Drone footage.
Home | AssetReel | 3D Walkthrough - loop + poster | n/a | 720x900 4:5 -> /video/asset-reel/3d-walkthrough.mp4 | /images/asset-reel/3d-walkthrough.jpg | None (placeholder) | Not Started | P1 | Muted 4s loop. Could be re-cut from the new Walkthrough footage.
Home | AssetReel | 3D Interior - still + poster | n/a | 720x900 4:5 -> /video/asset-reel/3d-interior.mp4 | /images/asset-reel/3d-interior.jpg | None (placeholder) | Not Started | P1 | Tagged 'Still frame' - a static render is fine. Could re-cut from new Renders footage.
Home | AssetReel | 3D Exterior - still + poster | n/a | 720x900 4:5 -> /video/asset-reel/3d-exterior.mp4 | /images/asset-reel/3d-exterior.jpg | None (placeholder) | Not Started | P1 | Tagged 'Still frame' - a static render is fine. Could re-cut from new Renders footage.
Home | AssetReel | Cinematic Film - loop + poster | n/a | 720x900 4:5 -> /video/asset-reel/cinematic-film.mp4 | /images/asset-reel/cinematic-film.jpg | None (placeholder) | Not Started | P1 | Muted 4s loop.
Home | AssetReel | Plot Superimposition - loop + poster | n/a | 720x900 4:5 -> /video/asset-reel/plot-superimposition.mp4 | /images/asset-reel/plot-superimposition.jpg | None (placeholder) | Not Started | P1 | Muted 4s loop.
Home | AssetReel | Vertical Reel - cut + poster | n/a | 9:16 (720x1280) -> /video/asset-reel/vertical-reel.mp4 | /images/asset-reel/vertical-reel.jpg | None (placeholder) | Not Started | P1 | Only 9:16 card in the row. ~15s cut.
Home | AssetReel | Microsite Loop - loop + poster | n/a | 720x900 4:5 -> /video/asset-reel/microsite-loop.mp4 | /images/asset-reel/microsite-loop.jpg | None (placeholder) | Not Started | P1 | Screen-capture loop of a live microsite.
Home | StatsBar | Google rating + 300+/120+ | n/a | n/a | n/a | Live Places API + hardcoded numbers | Done | P0 | No media asset. Rating is live; confirm 300+/120+ before launch.
Home | TrustStrip | RERA / DGCA / In-House / NDA pills | n/a | n/a | n/a | Lucide code icons (ShieldCheck, PlaneTakeoff, Building2, Lock) | Done | - | NO image asset needed - icons are drawn in code.
Home | ClientLogoWall | 11 client / partner logos | PNG, transparent, up to 300px wide | same (responsive) | n/a | 11 PNGs on disk (Laxmi + Western Arch named; partner-01..09 placeholder) | In Progress | P1 | Rename 9 placeholders with real brands. SVG monochrome preferred per roadmap.
Home | Services ScrollPin | Slide 1 - Drone & Aerial 360 | LIVE: /video/Drone and aerial 360 no text-desk.mp4 (10.7MB) | LIVE: /video/Drone and Aerial 360 portrait 01-mob.mp4 (10.5MB) | color tint only (no poster image) | Both REAL - wired into app/page.tsx | Done | P1 | Real footage landed. HEAVY (~21MB pair) - compress. Filename has spaces; rename to svc-drone*.mp4.
Home | Services ScrollPin | Slide 2 - Photoreal Renders | LIVE: /video/Renders with no text-desk.mp4 (3.4MB) | LIVE: /video/Renders potrait 02-mob.mp4 (2.0MB) | color tint only | Both REAL - wired into app/page.tsx | Done | P1 | Real footage landed. Good weight. Rename to svc-renders*.mp4 (typo 'potrait' + spaces).
Home | Services ScrollPin | Slide 3 - Cinematic Walkthroughs | LIVE: /video/Walkthrough with no text-desk.mp4 (11.3MB) | LIVE: /video/Walthrough partrait with no text-mob.mp4 (11.2MB) | color tint only | Both REAL - wired into app/page.tsx | Done | P1 | Real footage landed. HEAVY (~22MB pair) - compress. Typo 'Walthrough'; rename to svc-walkthrough*.mp4.
Home | Services ScrollPin | Slide 4 - 360 Virtual Tours | 1920x1080 -> /video/svc-tour.mp4 | 1080x1920 -> /video/svc-tour-mobile.mp4 | color tint only | Both = placeholder (intro-reel-web.mp4) | Not Started | P1 | STILL NEEDED. Next in line now that slides 1-3 have real footage.
Home | Services ScrollPin | Slide 5 - Films, Reels & Sites | 1920x1080 -> /video/svc-marketing.mp4 | 1080x1920 -> /video/svc-marketing-mobile.mp4 | color tint only | Both = placeholder (intro-reel-web.mp4) | Not Started | P1 | STILL NEEDED.
Home | Services ScrollPin | Slide 6 - Project Microsites | 1920x1080 -> /video/svc-microsite.mp4 | 1080x1920 -> /video/svc-microsite-mobile.mp4 | color tint only | Both = placeholder (intro-reel-web.mp4) | Not Started | P1 | STILL NEEDED.
Home | SolutionsRouter | Per-chip example thumbnails (6 types) | ~400x300 (optional) | (optional) | n/a | None - lucide icons in use | Optional | P3 | DEFERRED nice-to-have. Currently icon-driven; thumbnails not required.
Home | SelectedWork | 8 latest Instagram reels (LIVE) | n/a | 9:16 (pulled live from IG Graph API) | thumbnails from IG | Live API (4h ISR) | In Progress | P0 | Pending: rotate IG token, provision Vercel KV, set CRON_SECRET.
Home | SelectedWork - fallback | Fallback reel 1 (video + poster) | n/a | 9:16, 720w MP4, 10-20MB -> /video/reels-fallback/reel-1.mp4 | /reels-fallback/reel-1.jpg | None | Not Started | P1 | Also set real permalink + caption.
Home | SelectedWork - fallback | Fallback reel 2 (video + poster) | n/a | 9:16 -> /video/reels-fallback/reel-2.mp4 | /reels-fallback/reel-2.jpg | None | Not Started | P1 | + permalink + caption.
Home | SelectedWork - fallback | Fallback reel 3 (video + poster) | n/a | 9:16 -> /video/reels-fallback/reel-3.mp4 | /reels-fallback/reel-3.jpg | None | Not Started | P1 | + permalink + caption.
Home | SelectedWork - fallback | Fallback reel 4 (video + poster) | n/a | 9:16 -> /video/reels-fallback/reel-4.mp4 | /reels-fallback/reel-4.jpg | None | Not Started | P1 | + permalink + caption.
Home | SelectedWork - fallback | Fallback reel 5 (video + poster) | n/a | 9:16 -> /video/reels-fallback/reel-5.mp4 | /reels-fallback/reel-5.jpg | None | Not Started | P1 | + permalink + caption.
Home | SelectedWork - fallback | Fallback reel 6 (video + poster) | n/a | 9:16 -> /video/reels-fallback/reel-6.mp4 | /reels-fallback/reel-6.jpg | None | Not Started | P1 | + permalink + caption.
Home | GlobalPresence | Cosmic globe + studio/reach pins | n/a | n/a | n/a | Hand-rolled SVG / code | Done | - | No media asset.
Home | Testimonials | 3 client quotes (+ optional headshots) | n/a | n/a | 3x square headshots 400x400 -> /images/clients/{name}.jpg (optional) | Quotes = placeholder (fictional); headshots = none (initials fallback) | In Progress | P1 | Replace 3 fictional quotes with real ones. Headshots optional.
Home | OutcomeWidgets | Map / Countdown / Metric / Attribution / Ticker | n/a | n/a | n/a | Hand-rolled SVG / code (data placeholders) | Done | P1 | No media. Numbers in lib/outcomes.ts are // CONFIRM placeholders.
Home | QuoteToolPromo + Wizard | Quote engine band & flow | n/a | n/a | n/a | UI / code | Done | - | No media. Pricing in lib/quotePricing.ts is v2-draft placeholder.
Home | CtaSplit | Closing contact band | n/a | n/a | n/a | UI / code | Done | - | No media.
ABOUT PAGE
About | AboutStudioVideo (#studio) | Inside-the-Studio team film | LIVE: /video/StudioTeam.mp4 (14MB, 16:9) | 1080x1920 -> /video/StudioTeam-mobile.mp4 | StudioTeam-poster.jpg + StudioTeam-poster-mobile.jpg | Desktop = StudioTeam.mp4 (real); mobile reuses desktop; posters = intro-poster.jpg | In Progress | P1 | Desktop is DONE. Need portrait re-cut + 2 real posters. StudioTeam0.mp4 (5MB) unused.
About | Team grid | Discipline role/count tiles | n/a | n/a | n/a | Abstract gradient avatars (code) | Done | - | No photos in current build - just counts (3/12/4/4/3/2).
About | Story / Mission / Values / Offices / CTA | Editorial text sections | n/a | n/a | n/a | Text / code | Done | - | StoryTimeline 2023-25; no media.
About | [FUTURE - Phase 3] | Named leadership portraits (x6) | n/a | n/a | 6x square 400x400 -> /images/team/ | Not wired in code | Future | P3 | Roadmap Phase 3. NOT in current design (team uses count tiles).
About | [FUTURE - Phase 3] | Studio gear strip images (x4) | n/a | n/a | ~400x300 each | Not wired in code | Future | P3 | Roadmap Phase 3. NOT in current design.
OTHER PAGES (no media)
Services | Pillars + SolutionsRouter | Discipline catalogue | n/a | n/a | n/a | Text / UI | Done | - | No page-specific media.
Contact | Form + map caption | Contact form | n/a | n/a | n/a | Text / UI | Done | - | Project types now match the 6 confirmed.
Quote | QuoteWizard | 5-step quote flow | n/a | n/a | n/a | UI | Done | - | No media. Pricing placeholders pending finance.
Privacy | Static legal page | Privacy policy copy | n/a | n/a | n/a | Text | In Progress | P1 | Adapted from live studio.build91.in/privacy-policy.
Terms | Static legal page | Terms & conditions copy | n/a | n/a | n/a | Text | In Progress | P1 | Adapted from live studio.build91.in/termsconditions.
FUTURE / DISABLED
Home | [DISABLED] Process ScrollPin | 4 process slides (commented out) | 1920x1080 -> /video/proc-*.mp4 | 1080x1920 -> /video/proc-*-mobile.mp4 | color tint only | Placeholder (section commented out in app/page.tsx) | Future | P3 | 8 files if restored (brief/storyboard/production/launch x 2).
Work | [FUTURE - Phase 3] Case Studies | 3 studies: hero + gallery each | hero ~1200x800 | n/a | 4-6 gallery images per study | Not wired (/work redirects to home) | Future | P3 | No component yet. Roadmap Phase 3.
BRAND ASSETS
Global | Logos | Build91 brand logos | n/a | n/a | n/a | B91StudioLogo1/2.png + Build91Logo_circle.png on disk | Done | - | Header/footer brand marks present.

## Summary
Content Asset Tracker - Summary
By Status |  | By Priority
Done |  | P0 - Critical
In Progress |  | P1 - High
Not Started |  | P2 - Medium
Future / Deferred |  | P3 - Low / Future
Optional
Total deliverables
Legend
Done | Built & live (asset may still need optimising - see notes)
In Progress | Partially done / pending swap or confirmation
Not Started | Asset still needs to be produced
Future | Phase 3+ / disabled - not in current build
Optional | Nice-to-have, not required
Latest change
Services slides 1-3 (Drone & Aerial 360, Photoreal Renders, Cinematic Walkthroughs) now have REAL landscape + portrait footage wired into app/page.tsx. Slides 4-6 (360 Tours, Marketing Stack, Microsites) are still on the intro-reel placeholder. Drone and Walkthrough pairs are ~21-22MB each - compress before launch (DoD: LCP < 2.5s). Filenames contain spaces/typos; rename to the svc-*.mp4 convention. Cross-checked against live code on the v2 branch.